## Sheet1
Who Reported | Date Reported | Description of Defect | Date Fixed | Who Fixed | Description of Fix
Regan | 2021-11-09 | When login is successful, index.html doesnt open | 2021-11-10 | Regan | We decided to get rid of the user login since it is saved on local storage
Regan | 2021-11-12 | index.html formatted messed up from last push | 2021-11-14 | Regan | Used CSS elements to fix the float elements. It still isn't perfect but its better
Natasha | 2021-11-14 | save user input workouts | 2021-11-16 | Natasha | added to local storage
Natasha | 2021-11-14 | Load in user input workouts | 2021-11-16 | Natasha | Saved to local storage
Natasha | 2021-11-14 | move select a day to home page and create new page for viewing old info | 2021-11-18 | All
Natasha | 2021-11-14 | add overall save button on day page | 2021-11-16 | Natasha | Added save functionality
Regan | 2021-11-15 | Workout display not showing up properly | 2021-11-15 | Regan | Used CSS elements fix the issue. There was a padding element that didn't need to be used
Jui | 2021-11-15 | When inputting something other than words for any log, like numbers or other characters, it does not give an error message saying that incorrect value entered.
Jui | 2021-11-15 | For the places where you can enter text as description, when clicked the default message does not go away automatically.
Natasha | 2021-11-16 | Water Tracker on monday.html reloads page when buttons are pressed | 2021-11-16 | Regan | Moved the </form> element before the buttons.
Regan | 2021-11-16 | When hitting enter on the food list it reloads the page | 2021-11-16 | Regan | Removed the </form> element
Natasha | 2021-11-16 | When save works, water tracker doesn't work. When water tracker works, save doesn't work | 2021-11-16 | Natasha | changed the Id being used
Regan | 2021-11-17 | Day.html doesnt have all links working at top | 2021-11-17 | Regan | Fixed the html linking
Regan | 2021-11-17 | Save the selected activity input for index.html | 2021-11-17 | Natasha | created a seperate javascript page with a function to save the input
Regan | 2021-11-17 | Reload the selected input when returing to index.html | 2021-11-17 | Natasha | created a seperate javascript page with a function to reload saved input
Natasha | 2021-11-17 | app.js throws an error with the object.html for the slider because it is null. need to set default to 5 | 2021-11-17 | Natasha | added if statements to prevent null errors on index.html
Regan | 2021-11-17 | food tracker stopped working | 2021-11-17 | Natasha | removed link from index to javascript and removed if statements that prevented null